## Dashboard
0.55
Essence Alpha Assessment
Project progress & performance — kernel + practices, measured by alpha state · assessed at the Solution level (see the Levels of Scale tab) | [6 empty] | 14
121
OVERALL COMPLETION |  | ALPHAS COMPLETE |  | CHECKLIST ITEMS |  |  | 220
55% |  | 1 / 14 |  | 121 / 220
ALPHA | OWNER | LEVEL | CURRENT STATE | PROGRESS | TARGET STATE | STATUS
CUSTOMER
Opportunity | Kernel | Solution | Value Established | 65.22% | Benefit Accrued | ● In progress
Stakeholders | Kernel | Solution | In Agreement | 78.95% | Satisfied in Use | ● In progress
Business Scenario | Business Scenarios | Enterprise | Released | 100% | Released | ✔ Complete
Service Blueprint | Service Blueprint | Solution | Blueprinted | 70% | In Operation | ● In progress
SOLUTION
Requirements | Kernel | Solution | Bounded | 56.67% | Fulfilled | ● In progress
System | Kernel | Solution | Not started | 0% | Operational | ○ Not started
Architectural Drivers | MVA | Solution | Quantified | 70% | Sustained | ● In progress
Architecture | MVA | Solution | Demonstrated | 63.64% | Established | ● In progress
Architecture Decisions | MVA | Solution | Communicated | 80% | Validated | ● In progress
Paved Road | MVA | Enterprise | Established | 50% | Pervasive | ● In progress
ENDEAVOR
Work | Kernel | Solution | Prepared | 57.89% | Closed | ● In progress
Team | Kernel | Solution | Formed | 64.71% | Performing | ● In progress
Way of Working | Kernel | Solution | Foundation Established | 41.18% | Working Well | ● In progress
Governance | MVG | Spans | Guiding | 70% | Effective | ● In progress
Tip: open any alpha tab and tick the ✔ column (dropdown) per checklist item. Current state, progress and this dashboard update automatically. • Sample data shown — clear the ✔ cells to start your own assessment.
Status: ✔ Complete ● In progress ○ Not started Level: Enterprise (inherited) · Solution (owned here) · Spans
→ See the 'Levels of Scale' tab for how the levels work

## Levels of Scale
Levels of Scale — naming the System
The System alpha is the system of interest — and it is fractal. Choose the level before you assess.
An enterprise is a system of systems; a solution is a sub-system of the enterprise; a configured product is a sub-system of the solution. The same kernel and practices instantiate at any level — and what is a System at one level is a sub-system at the level above. The boundary you draw decides what every alpha actually measures.
ENTERPRISE — System = the enterprise Enterprise architecture, the paved road, drivers and standing governance are owned here. Each solution rolls up into the enterprise.
SOLUTION / PROJECT — System = the solution Inherits the enterprise paved road, drivers and governance as context; owns the architecture and decisions for this solution.
COMPONENT — System = a configured product A sub-system of the solution, tracked in its own right when it warrants it.
The same kernel + practices run at each level; a System at one level is a sub-system at the one above.
WHICH PRACTICE RUNS WHERE
ENTERPRISE → | Business Scenarios (set the drivers) · enterprise MVA · MVG (guardrails + paved road) — handed down as context
SOLUTION → | Service Blueprint (design the service) · MVA (architect within the guardrails) — feeds evidence & new drivers back up
This workbook assesses the SOLUTION level. Alphas owned here are tagged Solution; the Paved Road and the (enterprise) Business Scenario are inherited from the Enterprise; Governance spans levels. The level tag appears on each alpha tab (top-right) and in the dashboard.

## Opportunity
← Dashboard | [8 empty] | 15
Opportunity |  |  | SOLUTION | [5 empty] | 23
The circumstances that make a new or changed system worthwhile. | [8 empty] | 3
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 3
Value Established | 65.22% | 3 / 6 | Kernel · Customer
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Identified | ✔ | An idea for improving the way of working, increasing market share or applying a new system has been identified. | 3 / 3 | Identified | 3 | 3 | 1 | 1
| ✔ | At least one stakeholder wishes to invest in understanding the opportunity and its value. |  | Solution Needed | 5 | 5 | 1 | 1
| ✔ | The other stakeholders who share the opportunity have been identified. |  | Value Established | 5 | 5 | 1 | 1
2. Solution Needed | ✔ | The stakeholders in the opportunity and the proposed solution have been identified. | 5 / 5 | Viable | 2 | 5 | 0 | 0
| ✔ | The stakeholder needs that generate the opportunity have been established. |  | Addressed | 0 | 3 | 0 | 0
| ✔ | Any underlying problems and their root causes have been identified. |  | Benefit Accrued | 0 | 2 | 0 | 0
| ✔ | It has been confirmed that a system-based solution is needed.
| ✔ | At least one solution has been proposed.
3. Value Established | ✔ | The value of addressing the opportunity has been quantified. | 5 / 5
| ✔ | The impact of the solution on the stakeholders is understood.
| ✔ | The value the system offers to those who fund and use it is understood.
| ✔ | The success criteria for the deployment are clear.
| ✔ | The desired outcomes are clear and quantified.
4. Viable | ✔ | A solution has been outlined. | 2 / 5
| ✔ | The solution can be developed and deployed within the constraints.
The risks associated with the solution are acceptable and manageable.
The ball-park costs are less than the anticipated value of the opportunity.
It is clear that pursuing the opportunity is viable.
5. Addressed |  | A usable system that demonstrably addresses the opportunity is available. | 0 / 3
The stakeholders agree the available solution is worth deploying.
The stakeholders are satisfied the solution addresses the opportunity.
6. Benefit Accrued |  | The solution has started to accrue benefits for the stakeholders. | 0 / 2
The return-on-investment is at least as good as anticipated.

## Stakeholders
← Dashboard | [8 empty] | 15
Stakeholders |  |  | SOLUTION | [5 empty] | 19
The people and groups that affect or are affected by the system. | [8 empty] | 4
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 4
In Agreement | 78.95% | 4 / 6 | Kernel · Customer
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Recognized | ✔ | The stakeholder groups are identified. | 3 / 3 | Recognized | 3 | 3 | 1 | 1
| ✔ | The key stakeholder groups are represented. |  | Represented | 4 | 4 | 1 | 1
| ✔ | The responsibilities of the stakeholder representatives are defined. |  | Involved | 3 | 3 | 1 | 1
2. Represented | ✔ | The representatives have agreed their responsibilities. | 4 / 4 | In Agreement | 5 | 5 | 1 | 1
| ✔ | The representatives are authorized to carry out their responsibilities. |  | Satisfied for Deployment | 0 | 2 | 0 | 0
| ✔ | The collaboration approach among representatives is agreed. |  | Satisfied in Use | 0 | 2 | 0 | 0
| ✔ | The team's way of working is supported and respected by the stakeholders.
3. Involved | ✔ | The representatives assist the team in line with their responsibilities. | 3 / 3
| ✔ | The representatives provide feedback and take decisions in a timely manner.
| ✔ | Changes are promptly communicated to the team and stakeholders.
4. In Agreement | ✔ | The minimal expectations of the stakeholder groups are agreed. | 5 / 5
| ✔ | The representatives are happy with their involvement.
| ✔ | The representatives' input is valued by the team.
| ✔ | The team's input is valued by the representatives.
| ✔ | Priorities are clear and perspectives balanced.
5. Satisfied for Deployment |  | The representatives provide feedback on the system from their group's perspective. | 0 / 2
The representatives confirm the system is ready for deployment.
6. Satisfied in Use |  | The stakeholders are using the system and providing feedback. | 0 / 2
The stakeholders confirm the system meets their expectations.

## Requirements
← Dashboard | [8 empty] | 17
Requirements |  |  | SOLUTION | [5 empty] | 30
What the system must do to address the opportunity and satisfy the stakeholders. | [8 empty] | 2
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 2
Bounded | 56.67% | 2 / 6 | Kernel · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Conceived | ✔ | The initial stakeholders agree a system is to be produced. | 4 / 4 | Conceived | 4 | 4 | 1 | 1
| ✔ | The stakeholders that will use the system are identified. |  | Bounded | 9 | 9 | 1 | 1
| ✔ | The stakeholders that will fund the initial work are identified. |  | Coherent | 4 | 7 | 0 | 0
| ✔ | There is a clear opportunity for the system to address. |  | Acceptable | 0 | 4 | 0 | 0
2. Bounded | ✔ | The stakeholders involved in developing the system are identified. | 9 / 9 | Addressed | 0 | 3 | 0 | 0
| ✔ | The stakeholders agree on the purpose of the system. |  | Fulfilled | 0 | 3 | 0 | 0
| ✔ | It is clear what success is for the system.
| ✔ | There is a shared understanding of the extent of the solution.
| ✔ | The way the requirements will be described is agreed.
| ✔ | The mechanisms for managing requirements are in place.
| ✔ | The prioritization scheme is clear.
| ✔ | Constraints are identified and considered.
| ✔ | Assumptions are clearly stated.
3. Coherent | ✔ | The requirements are captured and shared with team and stakeholders. | 4 / 7
| ✔ | The origin and rationale of the requirements are clear.
| ✔ | Conflicting requirements are identified and addressed.
| ✔ | The requirements convey the essential characteristics of the system.
The most important usage scenarios can be explained.
The priority of the requirements is clear.
The team understands what must be delivered and agrees to deliver it.
4. Acceptable |  | The stakeholders accept the requirements describe an acceptable solution. | 0 / 4
The rate of change to agreed requirements is low and under control.
The value of implementing the requirements is clear.
The requirements are testable.
5. Addressed |  | Enough requirements are addressed for the system to be acceptable. | 0 / 3
The implemented requirement items provide clear value.
The system is accepted by the stakeholders as worth making operational.
6. Fulfilled |  | The stakeholders accept the requirements capture what they need. | 0 / 3
No outstanding requirement items prevent acceptance.
The system fully satisfies the requirements.

## System
← Dashboard | [8 empty] | 0
System |  |  | SOLUTION | [5 empty] | 31
The system that delivers value — software, configured products, hardware, data and services. A generalisation of Essence's Software System. | [8 empty] | 0
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 0
Not started | 0% | 0 / 6 | Kernel · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Architecture Selected |  | The criteria for selecting the architecture are agreed. | 0 / 7 | Architecture Selected | 0 | 7 | 0 | 0
|  | The architecture's key concepts and properties are clearly defined. |  | Demonstrable | 0 | 6 | 0 | 0
|  | The selected architecture is clearly conceived. |  | Usable | 0 | 7 | 0 | 0
|  | The system boundary is known. |  | Ready | 0 | 4 | 0 | 0
|  | Significant decisions about the system's organization have been made. |  | Operational | 0 | 3 | 0 | 0
|  | Buy, build, and reuse decisions have been made. |  | Retired | 0 | 4 | 0 | 0
The key technical risks are agreed.
2. Demonstrable |  | The key architectural characteristics have been demonstrated. | 0 / 6
The system can be exercised and its performance measured.
Critical configurations of the architecture have been demonstrated.
Critical interfaces have been demonstrated.
Integration with other existing systems has been demonstrated.
Relevant stakeholders agree the demonstrated architecture is appropriate.
3. Usable |  | The system can be operated by the stakeholders who use it. | 0 / 7
The functionality provided by the system has been tested.
The system's performance is acceptable to the stakeholders.
Defect levels are acceptable to the stakeholders.
The system is sufficiently documented.
The released system elements are known.
The added value provided by the system is clear.
4. Ready |  | Documentation on deploying and using the system in its intended environment is available. | 0 / 4
The stakeholder representatives accept the system as fit-for-purpose.
The stakeholder representatives want to make the system available for use.
Operational support is in place.
5. Operational |  | The system has been made available to its intended stakeholders. | 0 / 3
At least one instance of the system is fully operational.
The system is fully supported to the agreed service levels.
6. Retired |  | The system has been replaced or discontinued. | 0 / 4
The system is no longer supported.
There are no official stakeholders still using the system.
Updates to the system will no longer be produced.

## Work
← Dashboard | [8 empty] | 11
Work |  |  | SOLUTION | [5 empty] | 19
The activity and effort applied to produce the result. | [8 empty] | 2
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 2
Prepared | 57.89% | 2 / 6 | Kernel · Endeavor
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Initiated | ✔ | The constraints and funding context are clear. | 4 / 4 | Initiated | 4 | 4 | 1 | 1
| ✔ | The sponsors are identified. |  | Prepared | 5 | 5 | 1 | 1
| ✔ | The priority is clear. |  | Started | 2 | 3 | 0 | 0
| ✔ | The work has been requested. |  | Under Control | 0 | 3 | 0 | 0
2. Prepared | ✔ | A credible plan and estimate are in place. | 5 / 5 | Concluded | 0 | 2 | 0 | 0
| ✔ | Funding and resources are committed. |  | Closed | 0 | 2 | 0 | 0
| ✔ | Key risks are identified and being addressed.
| ✔ | The criteria for success are agreed.
| ✔ | Governance and the way of working are in place.
3. Started | ✔ | The work has started and progress is being monitored. | 2 / 3
| ✔ | The team is performing the work.
Tasks are being completed.
4. Under Control |  | Tasks are being completed and risks are under control. | 0 / 3
Estimates are updated and re-work is under control.
Measures of progress and velocity are available.
5. Concluded |  | The work to produce the results has concluded. | 0 / 2
The results have been achieved and accepted by the stakeholders.
6. Closed |  | Everything has been archived and lessons captured. | 0 / 2
The budget is reconciled and the team released.

## Team
← Dashboard | [8 empty] | 11
Team |  |  | SOLUTION | [5 empty] | 17
The group actively developing, maintaining and supporting the system. | [8 empty] | 2
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 2
Formed | 64.71% | 2 / 5 | Kernel · Endeavor
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Seeded | ✔ | The team mission is defined. | 5 / 5 | Seeded | 5 | 5 | 1 | 1
| ✔ | The constraints on the team are known. |  | Formed | 4 | 4 | 1 | 1
| ✔ | The required competencies are identified. |  | Collaborating | 2 | 3 | 0 | 0
| ✔ | The leadership and governance model is selected. |  | Performing | 0 | 3 | 0 | 0
| ✔ | The team size and composition are agreed. |  | Adjourned | 0 | 2 | 0 | 0
2. Formed | ✔ | Enough team members are recruited to start. | 4 / 4
| ✔ | The roles and responsibilities are understood.
| ✔ | The members understand how to work together.
| ✔ | The members are committed.
3. Collaborating | ✔ | The team works as one cohesive unit. | 2 / 3
| ✔ | Communication is open and honest.
The team is focused on achieving the mission.
4. Performing |  | The team consistently meets its commitments. | 0 / 3
The team adapts to the changing context.
The team identifies and addresses problems without outside help.
5. Adjourned |  | The team's responsibilities have been handed over or fulfilled. | 0 / 2
The resources have been released.

## Way of Working
← Dashboard | [8 empty] | 7
Way of Working |  |  | SOLUTION | [5 empty] | 17
The tailored set of practices and tools the team uses to guide its work. | [8 empty] | 2
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 2
Foundation Established | 41.18% | 2 / 6 | Kernel · Endeavor
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Principles Established | ✔ | The principles and constraints are committed to by the team. | 3 / 3 | Principles Established | 3 | 3 | 1 | 1
| ✔ | The principles are agreed by the stakeholders. |  | Foundation Established | 3 | 3 | 1 | 1
| ✔ | The tool and practice needs are understood. |  | In Use | 1 | 3 | 0 | 0
2. Foundation Established | ✔ | The key practices and tools are selected and integrated enough to start. | 3 / 3 | In Place | 0 | 3 | 0 | 0
| ✔ | The non-negotiable practices are agreed. |  | Working Well | 0 | 3 | 0 | 0
| ✔ | The capability gaps are understood. |  | Retired | 0 | 2 | 0 | 0
3. In Use | ✔ | The practices and tools are in use by the team. | 1 / 3
The team is adapting the way of working to its needs.
Feedback mechanisms are in place.
4. In Place |  | The whole team is using the way of working. | 0 / 3
The team has access to the tools.
The way of working is regularly inspected.
5. Working Well |  | The team predictably delivers using the way of working. | 0 / 3
The practices are applied naturally and tuned continuously.
The team continuously improves the way of working.
6. Retired |  | The way of working is no longer in use. | 0 / 2
The lessons learned have been captured.

## Architectural Drivers
← Dashboard | [8 empty] | 7
Architectural Drivers |  |  | SOLUTION | [5 empty] | 10
The significant concerns, goals, constraints and quality attributes that shape the architecture. | [8 empty] | 3
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 3
Quantified | 70% | 3 / 5 | MVA · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Identified | ✔ | The architecturally-significant concerns and their owners are surfaced. | 2 / 2 | Identified | 2 | 2 | 1 | 1
| ✔ | A candidate list of drivers exists. |  | Prioritised | 2 | 2 | 1 | 1
2. Prioritised | ✔ | The significant few drivers are agreed and ranked. | 2 / 2 | Quantified | 2 | 2 | 1 | 1
| ✔ | The trivial many are explicitly deferred. |  | Addressed | 1 | 2 | 0 | 0
3. Quantified | ✔ | Each significant driver has a measurable success criterion. | 2 / 2 | Sustained | 0 | 2 | 0 | 0
| ✔ | The criteria are agreed with the stakeholders.
4. Addressed | ✔ | The drivers are reflected in the decisions and the architecture. | 1 / 2
Evidence shows the drivers are being met.
5. Sustained |  | The drivers are monitored as the context changes. | 0 / 2
The drivers are re-validated and updated when needed.

## Architecture
← Dashboard | [8 empty] | 7
Architecture |  |  | SOLUTION | [5 empty] | 11
The minimum set of structures, building blocks and views needed to satisfy the significant drivers and enable delivery. | [8 empty] | 3
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 3
Demonstrated | 63.64% | 3 / 6 | MVA · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Envisioned | ✔ | The target direction, scope and value are agreed on a page. | 2 / 2 | Envisioned | 2 | 2 | 1 | 1
| ✔ | The key stakeholders share the vision. |  | Outlined | 2 | 2 | 1 | 1
2. Outlined | ✔ | The minimum viable structure, boundaries and interfaces are defined. | 2 / 2 | Demonstrated | 2 | 2 | 1 | 1
| ✔ | Only the building blocks needed now are included. |  | Usable | 1 | 2 | 0 | 0
3. Demonstrated | ✔ | The riskiest parts are proven via spike, reference or increment. | 2 / 2 | Established | 0 | 1 | 0 | 0
| ✔ | The key decisions are validated by evidence. |  | Evolving | 0 | 2 | 0 | 0
4. Usable | ✔ | The architecture is actively guiding and constraining delivery. | 1 / 2
The teams are building within it.
5. Established |  | The architecture is in operation and delivering the intended outcomes. | 0 / 1
6. Evolving |  | The architecture is changing under managed, continuous adaptation. | 0 / 2
Change is handled without big-bang rework.

## Architecture Decisions
← Dashboard | [8 empty] | 4
Architecture Decisions |  |  | SOLUTION | [5 empty] | 5
The significant, costly-to-reverse choices that are the architecture. | [8 empty] | 4
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 4
Communicated | 80% | 4 / 5 | MVA · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Needed | ✔ | A significant, costly-to-reverse decision point is recognised and owned. | 1 / 1 | Needed | 1 | 1 | 1 | 1
2. Framed | ✔ | The options, trade-offs and the last responsible moment are understood. | 1 / 1 | Framed | 1 | 1 | 1 | 1
3. Decided | ✔ | The choice is made and recorded with rationale and consequences (ADR). | 1 / 1 | Decided | 1 | 1 | 1 | 1
4. Communicated | ✔ | The decision is known and accepted by those it affects. | 1 / 1 | Communicated | 1 | 1 | 1 | 1
5. Validated |  | The decision is proven by evidence and outcome, or revisited. | 0 / 1 | Validated | 0 | 1 | 0 | 0

## Paved Road
← Dashboard | [8 empty] | 5
Paved Road |  |  | ENTERPRISE | [5 empty] | 10
The reusable service chassis of approved products, patterns and standards that makes the compliant choice the easy one. | [8 empty] | 2
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 2
Established | 50% | 2 / 5 | MVA · Solution
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Seeded | ✔ | The need for a paved road is recognised. | 2 / 2 | Seeded | 2 | 2 | 1 | 1
| ✔ | A first approved default or two exists. |  | Established | 2 | 2 | 1 | 1
2. Established | ✔ | A coherent service chassis of approved products, patterns and standards is published. | 2 / 2 | Adopted | 1 | 2 | 0 | 0
| ✔ | The paved road is self-serviceable. |  | Pervasive | 0 | 2 | 0 | 0
3. Adopted | ✔ | Teams build on the paved road by default. | 1 / 2 | Evolving | 0 | 2 | 0 | 0
On-road choices need no review.
4. Pervasive |  | The paved road is the norm across the estate. | 0 / 2
Going off-road is the rare, justified exception.
5. Evolving |  | The paved road is continuously widened and pruned. | 0 / 2
Learnings from reviews feed back into it.

## Governance
← Dashboard | [8 empty] | 7
Governance |  |  | SPANS LEVELS | [5 empty] | 10
The lightweight decision rights, guardrails and assurance that keep delivery aligned with intent. | [8 empty] | 3
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 3
Guiding | 70% | 3 / 5 | MVG · Endeavor
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Initiated | ✔ | The decision rights and minimal guardrails are agreed. | 2 / 2 | Initiated | 2 | 2 | 1 | 1
| ✔ | It is clear who decides what. |  | Engaged | 2 | 2 | 1 | 1
2. Engaged | ✔ | A lean governance cadence operates. | 2 / 2 | Guiding | 2 | 2 | 1 | 1
| ✔ | The teams know the guardrails. |  | Assured | 1 | 2 | 0 | 0
3. Guiding | ✔ | Decisions flow within the guardrails. | 2 / 2 | Effective | 0 | 2 | 0 | 0
| ✔ | Only exceptions are escalated.
4. Assured | ✔ | Conformance is evidenced where it genuinely matters. | 1 / 2
The architecture reviews are acted upon.
5. Effective |  | Governance demonstrably enables delivery. | 0 / 2
The governance itself is continuously tuned and lightened.

## Business Scenario
← Dashboard | [8 empty] | 8
Business Scenario |  |  | ENTERPRISE | [5 empty] | 8
The structured understanding of the business need, progressing through the method's phases until it can drive the architecture. | [8 empty] | 4
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 4
Released | 100% | 4 / 4 | Business Scenarios · Customer
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Premise Formed | ✔ | The business premise — problem, environment and objectives — is captured. | 2 / 2 | Premise Formed | 2 | 2 | 1 | 1
| ✔ | The customer and their goal are clear. |  | Verified | 2 | 2 | 1 | 1
2. Verified | ✔ | The five elements (problem, environment, outcomes, human and system actors) are gathered. | 2 / 2 | Refined | 2 | 2 | 1 | 1
| ✔ | An initial model is verified with the stakeholders. |  | Released | 2 | 2 | 1 | 1
3. Refined | ✔ | The objectives are made SMART. | 2 / 2
| ✔ | The scenario is refined to fit-for-purpose with the stakeholders.
4. Released | ✔ | The Business Scenario is documented and signed off. | 2 / 2
| ✔ | It is ready to drive the architecture.

## Service Blueprint
← Dashboard | [8 empty] | 7
Service Blueprint |  |  | SOLUTION | [5 empty] | 10
A map of one service journey across all its layers, sliced and progressed like a use case. | [8 empty] | 3
CURRENT STATE | PROGRESS | STATES ACHIEVED | OWNER · AREA | [5 empty] | 3
Blueprinted | 70% | 3 / 5 | Service Blueprint · Customer
STATE | ✔ | CHECKLIST ITEM | STATE STATUS
1. Scoped | ✔ | The service journey and customer to blueprint are chosen and bounded. | 2 / 2 | Scoped | 2 | 2 | 1 | 1
| ✔ | The customer and their goal are clear. |  | Frontstage Mapped | 2 | 2 | 1 | 1
2. Frontstage Mapped | ✔ | The customer-actions row and frontstage touchpoints are laid out across the line of interaction. | 2 / 2 | Blueprinted | 2 | 2 | 1 | 1
| ✔ | The physical evidence is captured. |  | Validated | 1 | 2 | 0 | 0
3. Blueprinted | ✔ | Backstage actions and support processes / systems are added below the lines of visibility and internal interaction. | 2 / 2 | In Operation | 0 | 2 | 0 | 0
| ✔ | The blueprint is complete across all three lines.
4. Validated | ✔ | The blueprint is walked through with customers and staff. | 1 / 2
Fail points, waits and hand-offs are surfaced and agreed.
5. In Operation |  | The service is delivered to the blueprint. | 0 / 2
The blueprint is kept live as the service evolves.